## Dashboard
FORMIVA PROJECT MANAGEMENT DASHBOARD
Daily operating view ¦ Update Task Tracker and Daily Status; dashboard formulas update automatically ¦ v2.1 (PRD phase numbers, rebased calendar)
Total Tasks |  | Completed |  | Blocked |  | Avg Progress
90 |  | 0 |  | 0 |  | 0%
STATUS SUMMARY |  |  | PHASE SUMMARY
Not Started | 84 |  | Phase 0 Discovery | 9 | 0%
In Progress | 0 |  | Phase 1 Foundations | 19 | 0%
Blocked | 0 |  | Phase 2 Database | 7 | 0%
Done | 0 |  | Phase 3 Intake | 7 | 0%
On Hold | 6 |  | Phase 4 Review | 4 | 0%
Overdue or blocked (RED) | 0 |  | Phase 5 Workers | 5 | 0%
Due within 7 days (AMBER) | 9 |  | Phase 6 AI Engine | 7 | 0%
|  |  | Phase 7 Routing + E2E | 6 | 0%
|  |  | Phase 8 Editor (gated) | 2 | 0%
|  |  | Phase 9 Integrations | 4 | 0%
|  |  | Phase 10 Hardening | 16 | 0%
|  |  | Phase 11 Measure | 4 | 0%
NEXT GATE
Next gate date | 2026-10-03 | Next gate | Discovery gate
TODAY / DAILY STATUS
Today | 2026-09-20 | Current daily status | Not in range
Today focus | Log runs 21 Sep 2026 to 1 Jan 2027
NEXT ACTIONS
Use the Task Tracker filters to identify overdue, blocked and high-priority work. Update % Complete as a decimal (e.g., 50% or 0.5). Phase 8 and 9 tasks are On Hold until three paid pilots or a pilot request (ADR-05). Rebuilt for v2.1 on 20 September 2026: dates start Monday 21 September 2026.

## Lists
Task Status | Priority | Area | Owner | Daily Status
Not Started | Critical | Product | Founder
In Progress | High | AI Engine | AI Assistant
Blocked | Medium | Backend | Developer
Done | Low | Database | Designer
On Hold |  | Frontend | Advisor
|  | Workflow Builder | External Provider
|  | Integrations | Technical Reviewer
|  | Infrastructure | Counsel
Security
GTM
Founder Learning

## Task Tracker
ID | Phase | Area | Task | Description / Definition of Done | Owner | Priority | Status | Start Date | Due Date | % Complete | Dependencies | Next Action | Notes | Days Left | Health
F-001 | 0 | GTM | Interview 15-20 target firms | Same fields for every interview: recurring onboarding pain, tools, rework, time, willingness to pay. Wedge validated if 8 of 15 name the same rework problem. | Founder | Critical | Not Started | 2026-09-21 | 2026-10-03 | 0% |  | Build list of 40 target firms | Business Plan gate; Coding Plan Phase 0 | 13 | GREEN
F-002 | 0 | GTM | Recruit 3 committed design partners | Three firms willing to pilot employee onboarding (letter of intent or paid pilot commitment). | Founder | Critical | Not Started | 2026-09-21 | 2026-10-03 | 0% | F-001 | Ask at the end of every interview | Discovery gate | 13 | GREEN
F-003 | 0 | GTM | Baseline worksheet and 20-minute diagnostic script | Reusable worksheet measuring current onboarding time, rework and handoffs; script from Sales Strategy stage 1. | Founder | High | Not Started | 2026-09-21 | 2026-09-25 | 0% |  | Draft script | Use identical fields per interview | 5 | AMBER
F-004 | 0 | Product | Create private repository and decision log; record ADR-01 to ADR-12 | DECISIONS.md, ASSUMPTIONS.md, SECURITY.md committed; each ADR accepted or changed with a reason. | Founder | High | Not Started | 2026-09-21 | 2026-09-23 | 0% |  | Create repository | Review document section 5 | 3 | AMBER
F-005 | 0 | AI Engine | Generate and validate the 100-case synthetic corpus | Coding Plan Prompt 0.1. Watermarked, no valid ID numbers, 10 hostile files, deterministic seed, coverage report. | AI Assistant | Critical | Not Started | 2026-09-28 | 2026-10-02 | 0% |  | Paste master context block then Prompt 0.1 | Never real documents | 12 | GREEN
F-006 | 0 | Product | Agree routing matrix and document classes | Nine POC scenarios plus classes identity, address, education, employment, bank, tax, photo, other. | Founder | High | Not Started | 2026-09-28 | 2026-09-30 | 0% |  | Review POC routing matrix | Signed decision record | 10 | GREEN
F-007 | 0 | AI Engine | Pre-register benchmark thresholds | Coding Plan Prompt 0.2. Thresholds committed BEFORE any benchmark run; CI blocks later edits. | Founder | Critical | Not Started | 2026-10-01 | 2026-10-02 | 0% | F-005 | Fill preregistration.yaml | Prevents moving the goalposts | 12 | GREEN
F-008 | 0 | GTM | Discovery gate decision | At least 8 of 15 interviews name the same problem and 3 firms will pilot. If not, change ICP, offer or price before Phase 2. | Founder | Critical | Not Started | 2026-10-03 | 2026-10-03 | 0% | F-001,F-002 | Hold gate review | Milestone: Discovery gate | 13 | GREEN
F-009 | 0 | Security | Engage a freelance technical reviewer | Reviewer agreed for Phases 2, 5, 6, 7 and 10 pull requests (a few hours per phase). | Founder | High | Not Started | 2026-09-21 | 2026-10-02 | 0% |  | Shortlist 2-3 reviewers | Budget line needed | 12 | GREEN
F-010 | 1 | Infrastructure | Check OCI status of Server #1 | Is instance-20260530-1135 running? Shape, account type (Always Free or Pay-As-You-Go), Oracle emails since June 2026. | Founder | Critical | Not Started | 2026-09-21 | 2026-09-21 | 0% |  | Open OCI console | Review document finding F-01 | 1 | AMBER
F-011 | 1 | Infrastructure | Upgrade OCI to Pay-As-You-Go with budget alert | Account upgraded; budget alert set (for example INR 6,000 per month). | Founder | Critical | Not Started | 2026-09-21 | 2026-09-22 | 0% | F-010 | Upgrade account | ADR-08 | 2 | AMBER
F-012 | 1 | Infrastructure | Right-size VM1 and create VM2 | VM1 2 OCPU / 12 GB; VM2 4 OCPU / 16 GB (Ampere A1, India South). Retry other availability domains if capacity is short. | Founder | Critical | Not Started | 2026-09-22 | 2026-09-25 | 0% | F-011 | Resize VM1; create VM2 | ADR-01 | 5 | AMBER
F-013 | 1 | Security | Harden Server #1 | Key-only SSH, PasswordAuthentication no, PermitRootLogin no, replace NOPASSWD:ALL, no public port 22, automatic security updates. | Founder | Critical | Not Started | 2026-09-21 | 2026-09-24 | 0% |  | Add key, test second session, then disable passwords | Do BEFORE any data. Runbook host-hardening.md | 4 | AMBER
F-014 | 1 | Infrastructure | Configure VCN and network security groups | VM2 private subnet, no public IP; VM1 no inbound rules; only VM1 to VM2 port 8080. | Founder | Critical | Not Started | 2026-09-23 | 2026-09-25 | 0% | F-012 | Create NSGs | ADR-03 | 5 | AMBER
F-015 | 1 | Infrastructure | Docker, Compose and resource limits on both VMs | Docker running; log rotation; container memory and CPU limits. | Founder | High | Not Started | 2026-09-24 | 2026-09-28 | 0% | F-012 | Install Docker | Prompt 1.2 output | 8 | GREEN
F-016 | 1 | Infrastructure | Cloudflare Tunnel, Access and WAF | Tunnel to VM1 port 8000 (api.vishyxtechie.in); Access policy for admin routes; rate limits on the public form path. | Founder | High | Not Started | 2026-09-25 | 2026-09-29 | 0% | F-013 | Point tunnel at port 8000 | Existing tunnel reused | 9 | GREEN
F-017 | 1 | Infrastructure | Vercel Pro team and project | Pro plan (commercial use), Preview and Production separated, no production secrets in Preview. | Founder | High | Not Started | 2026-09-25 | 2026-09-29 | 0% |  | Create team | ADR-08 | 9 | GREEN
F-018 | 1 | Security | Clerk development and production instances | Sign-in configured, MFA for owners and admins, webhook endpoint with signing secret. | Founder | High | Not Started | 2026-09-28 | 2026-10-01 | 0% |  | Create instances | Authentication only | 11 | GREEN
F-019 | 1 | Infrastructure | R2 buckets and scoped tokens | formiva-quarantine, formiva-docs, formiva-backups; no public access; least-privilege token per bucket; lifecycle rules. | Founder | High | Not Started | 2026-09-28 | 2026-10-01 | 0% |  | Create buckets | Decision D-2 (data location) open | 11 | GREEN
F-020 | 1 | Integrations | Resend sending domain verified | SPF, DKIM and DMARC records in place; test email delivered. | Founder | Medium | Not Started | 2026-09-28 | 2026-10-02 | 0% |  | Add domain | Free-tier limits: verify | 12 | GREEN
F-021 | 1 | Security | GitHub protections and scanning | Branch protection on main, required checks, secret scanning, Dependabot. | Founder | High | Not Started | 2026-09-21 | 2026-09-25 | 0% | F-004 | Enable protections | MFA on all accounts | 5 | AMBER
F-022 | 1 | Security | Choose secrets approach and create inventory | SOPS with age or OCI Vault (decision D-4); secret inventory sheet with owners and rotation dates. | Founder | High | Not Started | 2026-09-28 | 2026-10-02 | 0% |  | Decide D-4 | Master-key custody plan | 12 | GREEN
F-023 | 1 | Infrastructure | Uptime and heartbeat monitoring | Service pinging /healthz with alert email (decision D-3); one test alert received. | Founder | Medium | Not Started | 2026-09-29 | 2026-10-02 | 0% | F-016 | Pick service | Verify free-tier limits | 12 | GREEN
F-024 | 1 | Backend | Monorepo scaffold and config validation | Coding Plan Prompt 1.1. make verify passes on a clean clone; config loader never echoes secrets. | AI Assistant | High | Not Started | 2026-09-24 | 2026-09-28 | 0% | F-004 | Run Prompt 1.1 | Master context block first | 8 | GREEN
F-025 | 1 | Infrastructure | Compose files for VM1 and VM2 | Coding Plan Prompt 1.2. No database or AI port published on 0.0.0.0. | AI Assistant | High | Not Started | 2026-09-25 | 2026-09-29 | 0% | F-024 | Run Prompt 1.2 | arm64 | 9 | GREEN
F-026 | 1 | Security | Host hardening script | Coding Plan Prompt 1.3. Idempotent, dry-run, refuses to lock out the operator. | AI Assistant | High | Not Started | 2026-09-22 | 2026-09-24 | 0% |  | Run Prompt 1.3 | Use for VM2 too | 4 | AMBER
F-027 | 1 | Security | CI pipeline | Coding Plan Prompt 1.4. Lint, tests, DB tests, secret scan, audits, semgrep, Trivy; fake secret must fail the build. | AI Assistant | High | Not Started | 2026-09-28 | 2026-10-01 | 0% | F-024 | Run Prompt 1.4 | Stable required-check names | 11 | GREEN
F-028 | 1 | Infrastructure | Phase 1 exit test and decision record | External port scan shows only Cloudflare-fronted HTTPS; health checks pass; no third VM or extra provider. | Founder | Critical | Not Started | 2026-10-02 | 2026-10-02 | 0% | F-013,F-014,F-016,F-025 | Run scan from outside | Appendix A record | 12 | GREEN
F-029 | 2 | Database | Apply migrations and run the 81 SQL checks | Delivered Formiva_DB_v2.1 applied locally and in CI; all checks pass. | AI Assistant | Critical | Not Started | 2026-10-05 | 2026-10-05 | 0% | F-028 | Copy migrations into packages/db | Coding Plan Phase 2 | 15 | GREEN
F-030 | 2 | Database | Create runtime roles and apply migrations on VM1 | LOGIN roles inheriting the four group roles; app role has no BYPASSRLS. | Founder | Critical | Not Started | 2026-10-06 | 2026-10-06 | 0% | F-029 | Create roles | Passwords from the secret store | 16 | GREEN
F-031 | 2 | Database | Database package: runner, withTenant, Drizzle types | Coding Plan Prompt 2.1. Checksummed migrations; no raw SQL outside packages/db. | AI Assistant | Critical | Not Started | 2026-10-05 | 2026-10-06 | 0% | F-029 | Run Prompt 2.1 | Reviewer required | 16 | GREEN
F-032 | 2 | Backend | Auth plugin: Clerk JWT, workspace selector, permissions | Coding Plan Prompt 2.2. Fails closed; header is only a selector. | AI Assistant | Critical | Not Started | 2026-10-06 | 2026-10-08 | 0% | F-031 | Run Prompt 2.2 | Reviewer required | 18 | GREEN
F-033 | 2 | Backend | Workspace bootstrap and members API | Coding Plan Prompt 2.3. Last owner protected; every change audited; OpenAPI drift check. | AI Assistant | High | Not Started | 2026-10-07 | 2026-10-08 | 0% | F-032 | Run Prompt 2.3 |  | 18 | GREEN
F-034 | 2 | Security | Tenant isolation negative suite from OpenAPI | Coding Plan Prompt 2.4. Every route tested with foreign IDs, no auth and low role; new routes covered automatically. | AI Assistant | Critical | Not Started | 2026-10-08 | 2026-10-09 | 0% | F-033 | Run Prompt 2.4 | Gate: tenant isolation | 19 | GREEN
F-035 | 2 | Security | Technical review and Phase 2 gate | Reviewer signs the Phase 2 pull requests and decision record. | Technical Reviewer | Critical | Not Started | 2026-10-09 | 2026-10-09 | 0% | F-034 | Send PR list | Milestone: Tenant isolation gate | 19 | GREEN
F-036 | 3 | Frontend | Form definition, publish flow and public renderer | Coding Plan Prompt 3.1. Mobile first; axe accessibility clean; published versions immutable. | AI Assistant | High | Not Started | 2026-10-12 | 2026-10-13 | 0% | F-035 | Run Prompt 3.1 | No ID-number fields | 23 | GREEN
F-037 | 3 | Backend | Respondent tokens, rate limits and consent | Coding Plan Prompt 3.2. Hash-only tokens; generic 404; consent before first value. | AI Assistant | Critical | Not Started | 2026-10-12 | 2026-10-14 | 0% | F-035 | Run Prompt 3.2 |  | 24 | GREEN
F-038 | 3 | Backend | Upload request and presigned quarantine upload | Coding Plan Prompt 3.3 (part 1). Size and type signed; 5-minute URL. | AI Assistant | Critical | Not Started | 2026-10-13 | 2026-10-14 | 0% | F-037 | Run Prompt 3.3 |  | 24 | GREEN
F-039 | 3 | Security | File-safety worker | Coding Plan Prompt 3.3 (part 2). Sniff, ClamAV, PDF/image/archive limits, promote or quarantine, scan evidence. | AI Assistant | Critical | Not Started | 2026-10-14 | 2026-10-15 | 0% | F-038 | Run Prompt 3.3 | Reviewer required | 25 | GREEN
F-040 | 3 | Backend | Submission transaction and value encryption | Coding Plan Prompt 3.4. Atomic; duplicate submit returns same case; ID numbers ciphertext only. | AI Assistant | Critical | Not Started | 2026-10-14 | 2026-10-15 | 0% | F-037 | Run Prompt 3.4 |  | 25 | GREEN
F-041 | 3 | Security | Hostile-file run and accessibility check | Every hostile corpus file quarantined; valid file promoted; friendly respondent messages. | Founder | Critical | Not Started | 2026-10-16 | 2026-10-16 | 0% | F-039,F-040 | Run corpus | Gate: intake and file safety | 26 | GREEN
F-042 | 3 | Security | Technical review of the upload pipeline | Reviewer signs Phase 3. | Technical Reviewer | Critical | Not Started | 2026-10-16 | 2026-10-16 | 0% | F-041 | Send PR list |  | 26 | GREEN
F-043 | 4 | Backend | Review-task API and corrections | Coding Plan Prompt 4.1. Optimistic lock, append-only corrections, superseding routing decision. | AI Assistant | High | Not Started | 2026-10-19 | 2026-10-20 | 0% | F-042 | Run Prompt 4.1 |  | 30 | GREEN
F-044 | 4 | Backend | Approvals, delegation, timeline and SLA timers | Coding Plan Prompt 4.2. Rejection needs a reason; incomplete approval returns 409. | AI Assistant | High | Not Started | 2026-10-20 | 2026-10-21 | 0% | F-043 | Run Prompt 4.2 |  | 31 | GREEN
F-045 | 4 | Frontend | Reviewer console | Coding Plan Prompt 4.3. Masked values, audited reveal, evidence highlights. | AI Assistant | High | Not Started | 2026-10-21 | 2026-10-22 | 0% | F-044 | Run Prompt 4.3 |  | 32 | GREEN
F-046 | 4 | Product | Phase 4 exit test | Reviewer resolves a low-confidence case; original AI result and evidence remain visible. | Founder | High | Not Started | 2026-10-23 | 2026-10-23 | 0% | F-045 | Demonstrate | Gate: review and approval | 33 | GREEN
F-047 | 5 | Backend | Worker loop, leases, reaper and scheduler | Coding Plan Prompt 5.1. Kill -9 test passes; dead letters visible. | AI Assistant | Critical | Not Started | 2026-10-26 | 2026-10-27 | 0% | F-046 | Run Prompt 5.1 | Reviewer required | 37 | GREEN
F-048 | 5 | Workflow Builder | Workflow JSON schema and step runner | Coding Plan Prompt 5.2. onboarding-v1 definition; published versions immutable. | AI Assistant | High | Not Started | 2026-10-27 | 2026-10-28 | 0% | F-047 | Run Prompt 5.2 | ADR-05 | 38 | GREEN
F-049 | 5 | Integrations | Integration executor, Resend adapter and webhook | Coding Plan Prompt 5.3. Success/transient/permanent/unknown; delivery status never proves the business action. | AI Assistant | Critical | Not Started | 2026-10-27 | 2026-10-29 | 0% | F-047 | Run Prompt 5.3 | Reviewer required | 39 | GREEN
F-050 | 5 | Backend | Chaos and duplicate-delivery tests | Coding Plan Prompt 5.4. Zero silent loss and zero duplicate effects on 3 consecutive runs. | AI Assistant | Critical | Not Started | 2026-10-29 | 2026-10-30 | 0% | F-049 | Run Prompt 5.4 |  | 40 | GREEN
F-051 | 5 | Security | Technical review and reliability gate | Reviewer signs Phase 5. | Technical Reviewer | Critical | Not Started | 2026-10-30 | 2026-10-30 | 0% | F-050 | Send PR list | Milestone: Reliability gate | 40 | GREEN
F-052 | 6 | AI Engine | AI Engine skeleton, contract v1.1 and signed requests | Coding Plan Prompt 6.1. Bytes-in design (ADR-12); no cloud credentials. | AI Assistant | Critical | Not Started | 2026-11-02 | 2026-11-02 | 0% | F-051 | Run Prompt 6.1 |  | 43 | GREEN
F-053 | 6 | AI Engine | OCR and language detection | Coding Plan Prompt 6.2. Text layer first; Tesseract English, Hindi, Tamil. | AI Assistant | High | Not Started | 2026-11-02 | 2026-11-03 | 0% | F-052 | Run Prompt 6.2 |  | 44 | GREEN
F-054 | 6 | AI Engine | Classification, extraction, grounding and scrubbing | Coding Plan Prompt 6.3. Injection-safe, no full ID numbers in output. | AI Assistant | Critical | Not Started | 2026-11-03 | 2026-11-04 | 0% | F-053 | Run Prompt 6.3 | Reviewer required | 45 | GREEN
F-055 | 6 | AI Engine | Confidence components and calibration | Coding Plan Prompt 6.4. Overall = minimum; uncalibrated classes route to review. | AI Assistant | Critical | Not Started | 2026-11-04 | 2026-11-05 | 0% | F-054 | Run Prompt 6.4 |  | 46 | GREEN
F-056 | 6 | AI Engine | Benchmark harness and model registry | Coding Plan Prompt 6.5. Refuses to run without pre-registration. | AI Assistant | Critical | Not Started | 2026-11-04 | 2026-11-05 | 0% | F-055 | Run Prompt 6.5 |  | 46 | GREEN
F-057 | 6 | AI Engine | Select model, record licence, run benchmark | Smallest passing model; licence checked; mixed-load run; ai_benchmark_runs row. | Founder | Critical | Not Started | 2026-11-05 | 2026-11-06 | 0% | F-056 | Register candidate | Decision D-1; Diwali 8 Nov | 47 | GREEN
F-058 | 6 | AI Engine | AI benchmark gate decision | PASS/FAIL against pre-registered thresholds; if fail, follow POC decision matrix. | Founder | Critical | Not Started | 2026-11-06 | 2026-11-06 | 0% | F-057 | Review report | Milestone: AI benchmark gate | 47 | GREEN
F-059 | 7 | Backend | Routing decision function and tests | Coding Plan Prompt 7.1. Pure function, reason codes, property tests, 100% branch coverage. | AI Assistant | Critical | Not Started | 2026-11-09 | 2026-11-10 | 0% | F-058 | Run Prompt 7.1 | Reviewer required | 51 | GREEN
F-060 | 7 | Backend | AI result transaction and review creation | Coding Plan Prompt 7.2. One transaction; retries never create duplicates. | AI Assistant | Critical | Not Started | 2026-11-10 | 2026-11-11 | 0% | F-059 | Run Prompt 7.2 |  | 52 | GREEN
F-061 | 7 | Backend | Post-approval pipeline | Coding Plan Prompt 7.3. Notify, confirm, audit; reconciliation of stuck cases. | AI Assistant | High | Not Started | 2026-11-11 | 2026-11-12 | 0% | F-060 | Run Prompt 7.3 |  | 53 | GREEN
F-062 | 7 | Product | End-to-end demonstration and evidence pack | Coding Plan Prompt 7.4. 100-case corpus, zero silent loss. | AI Assistant | Critical | Not Started | 2026-11-12 | 2026-11-13 | 0% | F-061 | Run Prompt 7.4 |  | 54 | GREEN
F-063 | 7 | Infrastructure | Backup and isolated restore proof | Encrypted backup restored into isolation; SQL suites and tenant tests pass. | Founder | Critical | Not Started | 2026-11-12 | 2026-11-13 | 0% | F-029 | Run backup script | POC exit requirement | 54 | GREEN
F-064 | 7 | Product | POC decision record | Proceed / change approach / not sensitive-pilot ready. Slip buffer weeks 9-10 available. | Founder | Critical | Not Started | 2026-11-16 | 2026-11-27 | 0% | F-062,F-063 | Fill sign-off sheet | Milestone: POC decision | 68 | GREEN
F-065 | 10 | Infrastructure | Backups and restore drill automation | Coding Plan Prompt 10.1. Corrupted backup fails the drill; backup-age alert. | AI Assistant | Critical | Not Started | 2026-11-30 | 2026-12-04 | 0% | F-064 | Run Prompt 10.1 |  | 75 | GREEN
F-066 | 10 | Security | Secret rotation and access review | Coding Plan Prompt 10.2. Dry-run rotation of the VM1-VM2 HMAC key succeeds. | AI Assistant | High | Not Started | 2026-12-07 | 2026-12-11 | 0% | F-064 | Run Prompt 10.2 |  | 82 | GREEN
F-067 | 10 | Infrastructure | Alerts and status page | Coding Plan Prompt 10.3. Every alert fired once and received. | AI Assistant | High | Not Started | 2026-12-07 | 2026-12-11 | 0% | F-064 | Run Prompt 10.3 | Thresholds from decision record | 82 | GREEN
F-068 | 10 | Backend | Retention, deletion and legal hold | Coding Plan Prompt 10.4. Proof of deletion; audit chain still verifies. | AI Assistant | High | Not Started | 2026-12-14 | 2026-12-18 | 0% | F-064 | Run Prompt 10.4 | Retention periods: decision D-6 | 89 | GREEN
F-069 | 10 | Security | Security test pack, ZAP and ASVS mapping | Coding Plan Prompt 10.5. High-severity findings block release. | AI Assistant | Critical | Not Started | 2026-12-14 | 2026-12-23 | 0% | F-064 | Run Prompt 10.5 |  | 94 | GREEN
F-070 | 10 | Security | Independent penetration test | Recommended before real employee data (decision D-7); scope: API, web, upload path, tenant isolation. | External Provider | Medium | Not Started | 2026-12-14 | 2027-01-15 | 0% | F-069 | Get quotes | Findings feed the gate | 117 | GREEN
F-071 | 10 | Security | Incident response drill | Severity-1 rehearsal from the SOP: contain, preserve evidence, 72-hour notice process. | Founder | High | Not Started | 2026-12-21 | 2026-12-23 | 0% | F-066 | Schedule drill |  | 94 | GREEN
F-072 | 10 | Security | Engage counsel | Processor terms, respondent notice and consent, retention, breach process, R2 location (decisions D-2, D-5, D-6). | Founder | Critical | Not Started | 2026-12-01 | 2027-02-26 | 0% |  | Shortlist Indian data-protection counsel | DPDP obligations from about 13 May 2027 | 159 | GREEN
F-073 | 10 | Security | Sensitive-pilot gate review and release v0.1.0 | All gate controls evidenced; counsel items answered; otherwise stay on synthetic or redacted data. | Founder | Critical | Not Started | 2026-12-28 | 2027-01-01 | 0% | F-065,F-066,F-067,F-068,F-069,F-071 | Hold gate meeting | Milestone: Sensitive-pilot gate | 103 | GREEN
F-074 | 10 | GTM | Pilot agreements and data terms | Written pilot scope, success measures, data terms; three firms. | Founder | Critical | Not Started | 2026-12-01 | 2027-01-08 | 0% | F-002 | Draft pilot one-pager | Sales Strategy stage 3 | 110 | GREEN
F-075 | 10 | GTM | Pilot 1 configured and running | Synthetic or redacted data until the gate allows real data; baseline measured before start. | Founder | High | Not Started | 2027-01-04 | 2027-02-05 | 0% | F-074 | Configure workspace |  | 138 | GREEN
F-076 | 10 | GTM | Pilot 2 configured and running | As pilot 1. | Founder | High | Not Started | 2027-01-11 | 2027-02-12 | 0% | F-074 | Configure workspace |  | 145 | GREEN
F-077 | 10 | GTM | Pilot 3 configured and running | As pilot 1. | Founder | High | Not Started | 2027-01-18 | 2027-02-19 | 0% | F-074 | Configure workspace |  | 152 | GREEN
F-078 | 10 | GTM | Convert pilots to paid and measure margin | Three paying logos and measured contribution margin. | Founder | Critical | Not Started | 2027-02-22 | 2027-03-26 | 0% | F-075,F-076,F-077 | Send conversion proposals | Milestone: Paid repeatability gate | 187 | GREEN
F-079 | 10 | Security | Counsel review of the trust evidence pack | Evidence pack v1 reviewed; open items tracked. | Counsel | Critical | Not Started | 2027-02-01 | 2027-02-26 | 0% | F-072 | Send pack | Milestone: Counsel review | 159 | GREEN
F-080 | 10 | GTM | Manual invoicing process and Razorpay decision | Manual billing for first pilots; decide when Razorpay adds enough value. | Founder | Medium | Not Started | 2027-01-11 | 2027-02-26 | 0% |  | Set up invoice template | Phase 9 dependency | 159 | GREEN
F-081 | 9 | Integrations | Signed outbound webhook adapter | Coding Plan Prompt 9.1. SSRF-safe; signature and replay window. | AI Assistant | Medium | On Hold | 2027-02-01 | 2027-02-12 | 0% | F-075 | Start only when a pilot asks | ADR-05 | 145 | GREEN
F-082 | 9 | Integrations | Google Sheets adapter | Coding Plan Prompt 9.2. Upsert by business key; reconciliation. | AI Assistant | Low | On Hold | 2027-02-15 | 2027-02-26 | 0% | F-075 | Start only when a pilot asks | ADR-05 | 159 | GREEN
F-083 | 9 | Integrations | Razorpay billing events | Coding Plan Prompt 9.3. Signature verified; event dedupe; reconciliation. | AI Assistant | Medium | On Hold | 2027-03-01 | 2027-03-12 | 0% | F-080 | Start when first pilot converts | ADR-05 | 173 | GREEN
F-084 | 9 | Integrations | 1,000-event reliability test | Coding Plan Prompt 9.4. No duplicate effects; unknown outcomes never replayed blindly. | AI Assistant | Medium | On Hold | 2027-03-15 | 2027-03-26 | 0% | F-081,F-082,F-083 | After adapters exist |  | 187 | GREEN
F-085 | 8 | Workflow Builder | Workflow linter and dry-run engine | Coding Plan Prompts 8.1 and 8.2. Dry-run never creates an executable interaction. | AI Assistant | Low | On Hold | 2027-04-05 | 2027-04-23 | 0% | F-078 | Start after 3 paid pilots | Gated by ADR-05 | 215 | GREEN
F-086 | 8 | Workflow Builder | Publish and rollback API and visual editor | Coding Plan Prompts 8.3 and 8.4. Rollback moves the active pointer; audited. | AI Assistant | Low | On Hold | 2027-04-26 | 2027-05-28 | 0% | F-085 | Start after linter | Gated by ADR-05 | 250 | GREEN
F-087 | 11 | Product | Analytics views and pilot report generator | Coding Plan Prompts 11.1 and 11.2. | AI Assistant | Medium | Not Started | 2027-04-05 | 2027-04-23 | 0% | F-078 | Run Prompts 11.1-11.2 |  | 215 | GREEN
F-088 | 11 | GTM | Measure activation and second-workflow demand | At least 60% of pilot customers request or activate a second workflow in writing. | Founder | High | Not Started | 2027-04-05 | 2027-05-14 | 0% | F-078 | Ask each customer | Expansion gate | 236 | GREEN
F-089 | 11 | Product | Decide first expansion pack | Leave, expense, IT, education, MSP or manufacturing based on evidence and 70% primitive-reuse gate. | Founder | High | Not Started | 2027-05-17 | 2027-05-31 | 0% | F-088 | Prepare decision memo | Milestone: Expansion decision | 253 | GREEN
F-090 | 11 | Security | DPDP commencement check | Confirm with counsel which obligations apply from about 13 May 2027 and that controls are in place. | Counsel | High | Not Started | 2027-05-03 | 2027-05-13 | 0% | F-072 | Book counsel session | Legal watch date | 235 | GREEN
Formulas:
Days Left = IF([Status]="Done",0,IF([Due Date]<TODAY(),"OVERDUE",[Due Date]-TODAY()))
Health = IF([Status]="Blocked","RED",IF([Status]="Done","GREEN",IF([Due Date]<TODAY(),"RED",IF([Due Date]-TODAY()<=7,"AMBER","GREEN"))))

## Daily Status
Date | Day | Overall Status | % Project Complete | Today’s Focus | Completed Today | Blockers / Risks | Decision Needed | Tomorrow’s Plan | Owner | Evidence / Link
2026-09-21 | Monday | Not Started | 0% | [5 empty] | Founder
2026-09-22 | Tuesday | Not Started | 0% | [5 empty] | Founder
2026-09-23 | Wednesday | Not Started | 0% | [5 empty] | Founder
2026-09-24 | Thursday | Not Started | 0% | [5 empty] | Founder
2026-09-25 | Friday | Not Started | 0% | [5 empty] | Founder
2026-09-26 | Saturday | Not Started | 0% | [5 empty] | Founder
2026-09-27 | Sunday | Not Started | 0% | [5 empty] | Founder
2026-09-28 | Monday | Not Started | 0% | [5 empty] | Founder
2026-09-29 | Tuesday | Not Started | 0% | [5 empty] | Founder
2026-09-30 | Wednesday | Not Started | 0% | [5 empty] | Founder
2026-10-01 | Thursday | Not Started | 0% | [5 empty] | Founder
2026-10-02 | Friday | Not Started | 0% | [5 empty] | Founder
2026-10-03 | Saturday | Not Started | 0% | [5 empty] | Founder
2026-10-04 | Sunday | Not Started | 0% | [5 empty] | Founder
2026-10-05 | Monday | Not Started | 0% | [5 empty] | Founder
2026-10-06 | Tuesday | Not Started | 0% | [5 empty] | Founder
2026-10-07 | Wednesday | Not Started | 0% | [5 empty] | Founder
2026-10-08 | Thursday | Not Started | 0% | [5 empty] | Founder
2026-10-09 | Friday | Not Started | 0% | [5 empty] | Founder
2026-10-10 | Saturday | Not Started | 0% | [5 empty] | Founder
2026-10-11 | Sunday | Not Started | 0% | [5 empty] | Founder
2026-10-12 | Monday | Not Started | 0% | [5 empty] | Founder
2026-10-13 | Tuesday | Not Started | 0% | [5 empty] | Founder
2026-10-14 | Wednesday | Not Started | 0% | [5 empty] | Founder
2026-10-15 | Thursday | Not Started | 0% | [5 empty] | Founder
2026-10-16 | Friday | Not Started | 0% | [5 empty] | Founder
2026-10-17 | Saturday | Not Started | 0% | [5 empty] | Founder
2026-10-18 | Sunday | Not Started | 0% | [5 empty] | Founder
2026-10-19 | Monday | Not Started | 0% | [5 empty] | Founder
2026-10-20 | Tuesday | Not Started | 0% | [5 empty] | Founder
2026-10-21 | Wednesday | Not Started | 0% | [5 empty] | Founder
2026-10-22 | Thursday | Not Started | 0% | [5 empty] | Founder
2026-10-23 | Friday | Not Started | 0% | [5 empty] | Founder
2026-10-24 | Saturday | Not Started | 0% | [5 empty] | Founder
2026-10-25 | Sunday | Not Started | 0% | [5 empty] | Founder
2026-10-26 | Monday | Not Started | 0% | [5 empty] | Founder
2026-10-27 | Tuesday | Not Started | 0% | [5 empty] | Founder
2026-10-28 | Wednesday | Not Started | 0% | [5 empty] | Founder
2026-10-29 | Thursday | Not Started | 0% | [5 empty] | Founder
2026-10-30 | Friday | Not Started | 0% | [5 empty] | Founder
2026-10-31 | Saturday | Not Started | 0% | [5 empty] | Founder
2026-11-01 | Sunday | Not Started | 0% | [5 empty] | Founder
2026-11-02 | Monday | Not Started | 0% | [5 empty] | Founder
2026-11-03 | Tuesday | Not Started | 0% | [5 empty] | Founder
2026-11-04 | Wednesday | Not Started | 0% | [5 empty] | Founder
2026-11-05 | Thursday | Not Started | 0% | [5 empty] | Founder
2026-11-06 | Friday | Not Started | 0% | [5 empty] | Founder
2026-11-07 | Saturday | Not Started | 0% | [5 empty] | Founder
2026-11-08 | Sunday | Not Started | 0% | [5 empty] | Founder
2026-11-09 | Monday | Not Started | 0% | [5 empty] | Founder
2026-11-10 | Tuesday | Not Started | 0% | [5 empty] | Founder
2026-11-11 | Wednesday | Not Started | 0% | [5 empty] | Founder
2026-11-12 | Thursday | Not Started | 0% | [5 empty] | Founder
2026-11-13 | Friday | Not Started | 0% | [5 empty] | Founder
2026-11-14 | Saturday | Not Started | 0% | [5 empty] | Founder
2026-11-15 | Sunday | Not Started | 0% | [5 empty] | Founder
2026-11-16 | Monday | Not Started | 0% | [5 empty] | Founder
2026-11-17 | Tuesday | Not Started | 0% | [5 empty] | Founder
2026-11-18 | Wednesday | Not Started | 0% | [5 empty] | Founder
2026-11-19 | Thursday | Not Started | 0% | [5 empty] | Founder
2026-11-20 | Friday | Not Started | 0% | [5 empty] | Founder
2026-11-21 | Saturday | Not Started | 0% | [5 empty] | Founder
2026-11-22 | Sunday | Not Started | 0% | [5 empty] | Founder
2026-11-23 | Monday | Not Started | 0% | [5 empty] | Founder
2026-11-24 | Tuesday | Not Started | 0% | [5 empty] | Founder
2026-11-25 | Wednesday | Not Started | 0% | [5 empty] | Founder
2026-11-26 | Thursday | Not Started | 0% | [5 empty] | Founder
2026-11-27 | Friday | Not Started | 0% | [5 empty] | Founder
2026-11-28 | Saturday | Not Started | 0% | [5 empty] | Founder
2026-11-29 | Sunday | Not Started | 0% | [5 empty] | Founder
2026-11-30 | Monday | Not Started | 0% | [5 empty] | Founder
2026-12-01 | Tuesday | Not Started | 0% | [5 empty] | Founder
2026-12-02 | Wednesday | Not Started | 0% | [5 empty] | Founder
2026-12-03 | Thursday | Not Started | 0% | [5 empty] | Founder
2026-12-04 | Friday | Not Started | 0% | [5 empty] | Founder
2026-12-05 | Saturday | Not Started | 0% | [5 empty] | Founder
2026-12-06 | Sunday | Not Started | 0% | [5 empty] | Founder
2026-12-07 | Monday | Not Started | 0% | [5 empty] | Founder
2026-12-08 | Tuesday | Not Started | 0% | [5 empty] | Founder
2026-12-09 | Wednesday | Not Started | 0% | [5 empty] | Founder
2026-12-10 | Thursday | Not Started | 0% | [5 empty] | Founder
2026-12-11 | Friday | Not Started | 0% | [5 empty] | Founder
2026-12-12 | Saturday | Not Started | 0% | [5 empty] | Founder
2026-12-13 | Sunday | Not Started | 0% | [5 empty] | Founder
2026-12-14 | Monday | Not Started | 0% | [5 empty] | Founder
2026-12-15 | Tuesday | Not Started | 0% | [5 empty] | Founder
2026-12-16 | Wednesday | Not Started | 0% | [5 empty] | Founder
2026-12-17 | Thursday | Not Started | 0% | [5 empty] | Founder
2026-12-18 | Friday | Not Started | 0% | [5 empty] | Founder
2026-12-19 | Saturday | Not Started | 0% | [5 empty] | Founder
2026-12-20 | Sunday | Not Started | 0% | [5 empty] | Founder
2026-12-21 | Monday | Not Started | 0% | [5 empty] | Founder
2026-12-22 | Tuesday | Not Started | 0% | [5 empty] | Founder
2026-12-23 | Wednesday | Not Started | 0% | [5 empty] | Founder
2026-12-24 | Thursday | Not Started | 0% | [5 empty] | Founder
2026-12-25 | Friday | Not Started | 0% | [5 empty] | Founder
2026-12-26 | Saturday | Not Started | 0% | [5 empty] | Founder
2026-12-27 | Sunday | Not Started | 0% | [5 empty] | Founder
2026-12-28 | Monday | Not Started | 0% | [5 empty] | Founder
2026-12-29 | Tuesday | Not Started | 0% | [5 empty] | Founder
2026-12-30 | Wednesday | Not Started | 0% | [5 empty] | Founder
2026-12-31 | Thursday | Not Started | 0% | [5 empty] | Founder
2027-01-01 | Friday | Not Started | 0% | [5 empty] | Founder

## Milestones
Milestone | Target Date | Success Measure | Status | % Complete | Owner | Notes
Discovery gate | 2026-10-03 | 8 of 15 interviews name the same problem; 3 firms committed to pilot | Not Started | 0% | Founder | Tasks F-001, F-002, F-008
Tenant isolation gate | 2026-10-09 | Delivered 81 SQL checks and the API cross-tenant suite pass; reviewer sign-off | Not Started | 0% | Founder | Tasks F-029 to F-035
Intake and file-safety gate | 2026-10-16 | Every hostile file quarantined; atomic submission; ID numbers ciphertext only | Not Started | 0% | Founder | Tasks F-036 to F-042
Review and approval gate | 2026-10-23 | Reviewer resolves an exception; original AI result preserved; approval guard proven | Not Started | 0% | Founder | Tasks F-043 to F-046
Reliability gate | 2026-10-30 | Zero silent loss and zero duplicate effects on 3 chaos runs | Not Started | 0% | Founder | Tasks F-047 to F-051
AI benchmark gate | 2026-11-06 | p50, p95, peak memory, queue age, accuracy, calibration recorded against pre-registered thresholds | Not Started | 0% | Founder | Tasks F-052 to F-058
POC decision | 2026-11-27 | Proceed / change approach / not sensitive-pilot ready, with evidence pack and restore proof | Not Started | 0% | Founder | Tasks F-059 to F-064
Sensitive-pilot gate | 2027-01-01 | Tenant isolation, encrypted restore, rotation, alerts, retention, incident drill all evidenced | Not Started | 0% | Founder | Tasks F-065 to F-073
Counsel review | 2027-02-26 | Processor terms, notice and consent, retention, breach process reviewed | Not Started | 0% | Founder | Tasks F-072, F-079
Paid repeatability gate | 2027-03-26 | 3 paying logos and measured contribution margin | Not Started | 0% | Founder | Tasks F-074 to F-078
DPDP commencement (watch date) | 2027-05-13 | Data Fiduciary obligations expected to commence; controls confirmed with counsel | Not Started | 0% | Founder | Task F-090
Expansion decision | 2027-05-31 | Evidence-backed decision on next pack; 60% second-workflow demand and 70% reuse gates | Not Started | 0% | Founder | Tasks F-087 to F-089

## Risks & Decisions
ID | Type | Risk / Decision | Impact | Probability | Mitigation / Next Step | Owner | Status | Review Date
R-001 | Risk | Oracle Always Free A1 allowance cut to 2 OCPU / 12 GB in total; Server #1 (4 OCPU / 24 GB) may be stopped or terminated; unpaid instances can be reclaimed | High | High | Check console now; upgrade to Pay-As-You-Go; budget alert; treat VMs as disposable and backups as the asset. | Founder | Open | 2026-09-25
R-002 | Risk | CPU-only AI on VM2 too slow or inaccurate for onboarding documents | High | Medium | Pre-registered benchmark; smallest passing model; bound concurrency; route to human review by default; no third VM. | Founder | Open | 2026-11-06
R-003 | Risk | AI classification or extraction error on sensitive documents | High | Medium | Evidence-first output, grounding check, per-class calibration, human review, no autonomous sensitive actions, database approval guard. | Founder | Open | 2026-10-20
R-004 | Risk | Too many industries dilute product and sales focus | High | High | Employee onboarding is the only launch wedge; paid-pilot and 70% reuse gates before any expansion. | Founder | Open | 2026-09-25
R-005 | Risk | Founder capacity is smaller than 12 phases of scope | High | High | Build order 0-7, 10, pilots; phases 8 and 9 gated (ADR-05); slip rules cut SLA timers, delegation and analytics first; hire a technical reviewer. | Founder | Open | 2026-10-09
R-006 | Risk | AI-generated code contains subtle security defects | High | Medium | CI gates, review checklist, generated IDOR suite, database as last line of defence, reviewer on phases 2, 3, 5, 6, 7, 10. | Founder | Open | 2026-10-09
R-007 | Risk | Server #1 compromised through SSH password login and NOPASSWD:ALL sudo user | High | Medium | Task F-013: key-only SSH, no root login, least-privilege sudo, no public port 22, fail2ban, MFA on cloud accounts. | Founder | Open | 2026-09-24
R-008 | Risk | DPDP Data Fiduciary obligations expected from about 13 May 2027 while pilots run | Medium | High | Consent and deletion built into schema; counsel engaged by February 2027; 72-hour breach process; processor terms. | Founder | Open | 2027-02-26
R-009 | Risk | Data-residency claim not supported: servers in India but R2 has no India-only location | Medium | Medium | Do not claim India-only residency; decide document store (decision D-2) before first pilot. | Founder | Open | 2026-10-01
R-010 | Risk | Data loss because backups fail silently or restore has never been tested | High | Medium | Nightly and 6-hourly encrypted backups, off-VM copy, backup-age alert, monthly restore drill as release gate. | Founder | Open | 2026-11-13
R-011 | Risk | Chosen model licence does not permit commercial use (licences differ by size within a family) | High | Medium | Check and record licence in the registry before benchmarking; alternatives ready. | Founder | Open | 2026-11-05
R-012 | Risk | Provider terms or free-tier limits change (Vercel Hobby non-commercial, Clerk, Resend, R2, OCI) | Medium | Medium | Vercel Pro; verify each provider at deployment and quarterly; cost model reviewed monthly. | Founder | Open | 2026-10-02
R-013 | Risk | Blended revenue per account of 3,200 is optimistic against the price ladder | Medium | High | Plan on 2,000 per account until pricing interviews say otherwise; implementation fees separate. | Founder | Open | 2026-10-03
R-014 | Risk | Pilot customers refuse to upload real employee documents or sales cycles are long | High | Medium | Synthetic or redacted pilots first; trust evidence pack; sensitive-pilot gate; partners as second channel. | Founder | Open | 2027-01-15
D-001 | Decision | ADR-01: VM1 = API, workers, PostgreSQL, ClamAV; VM2 = AI Engine only; no third VM | High | Low | Reverse by moving PostgreSQL back to VM2 (schema unchanged). | Founder | Decided | 2026-09-20
D-002 | Decision | ADR-02: REST with OpenAPI 3.1 (no tRPC) | Medium | Low | Contract generated from Zod schemas. | Founder | Decided | 2026-09-20
D-003 | Decision | ADR-03: VM1 to VM2 over private VCN with signed requests; Tunnel only for public ingress | Medium | Low | Use Tunnel plus Access service tokens if VMs are in different regions. | Founder | Decided | 2026-09-20
D-004 | Decision | ADR-04: PostgreSQL job dispatch (SKIP LOCKED); Valkey optional | Medium | Low | Add Valkey later for wake-up and rate limits only. | Founder | Decided | 2026-09-20
D-005 | Decision | ADR-05: workflows as versioned JSON; visual editor and extra adapters gated behind three paid pilots | Medium | Low | Start Phase 8 earlier only if a pilot requires it. | Founder | Decided | 2026-09-20
D-006 | Decision | ADR-06: one category sentence; retire "Universal Form-to-Workflow Platform" wording | Medium | Low | Keep universal as an internal architecture idea only. | Founder | Decided | 2026-09-20
D-007 | Decision | ADR-07: PRD phase numbers 0-11; build order 0-7, 10, pilots, 9, 8, 11 | Medium | Low | Dashboard rebuilt to match. | Founder | Decided | 2026-09-20
D-008 | Decision | ADR-08: OCI Pay-As-You-Go; Vercel Pro from the first customer | High | Low | Budget about US$70-80 per month fixed. | Founder | Decided | 2026-09-20
D-009 | Decision | ADR-09: customer document content processed only by the self-hosted AI Engine | High | Low | Managed AI only by explicit workspace opt-in under a signed data-processing agreement. | Founder | Decided | 2026-09-20
D-010 | Decision | ADR-10: SQL-first migrations with Drizzle for typed queries | Medium | Low | Delivered schema package is the source of truth. | Founder | Decided | 2026-09-20
D-011 | Decision | ADR-11: envelope encryption for highly sensitive values | High | Low | Master key outside the database (decision D-016). | Founder | Decided | 2026-09-20
D-012 | Decision | ADR-12: AI Engine holds no cloud credentials; worker sends verified bytes | Medium | Low | Reverse only with a read-only bucket token (not recommended). | Founder | Decided | 2026-09-20
D-013 | Decision | Open: AI model and size (technical decision D-1) | High | Medium | Benchmark candidates; smallest that passes; record licence. | Founder | Open | 2026-11-06
D-014 | Decision | Open: document store location (technical decision D-2) | Medium | Medium | Keep R2 without an India claim, or OCI Object Storage in the same region. | Founder | Open | 2026-10-01
D-015 | Decision | Open: monitoring and alerting service (technical decision D-3) | Low | Low | Free uptime and heartbeat service plus email; verify limits. | Founder | Open | 2026-10-02
D-016 | Decision | Open: secrets and master-key custody (technical decision D-4) | High | Medium | OCI Vault or SOPS with age. | Founder | Open | 2026-10-02
D-017 | Decision | Open: counsel engagement (technical decision D-5) | High | Medium | Indian data-protection lawyer by February 2027. | Founder | Open | 2026-12-01
D-018 | Decision | Open: retention periods, backup retention, deletion SLAs (technical decision D-6) | Medium | Medium | Counsel and customer input. | Founder | Open | 2026-12-14
D-019 | Decision | Open: independent penetration test (technical decision D-7) | Medium | Low | Budget and provider. | Founder | Open | 2026-12-14